## Burn Down Chart
Project: | Personal Store Application
Sprint # | 6
[5 empty] | DATE: | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Time Left
| N/A | Rework Form Styles | Adjusted Login for to better fit the application styles. | Marc | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Changed Registration form to match Login form. | " | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| N/A | Reviewed Application Documentation. | Updated documentations. | " | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0
| N/A | Walkthrough Presentation. | Recorded Final Presentation. | " | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 8 | 6.86 | 5.72 | 4.58 | 3.44 | 2.3 | 1.16 | 0.02
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 8 | 8 | 6 | 3 | 3 | 3 | 3 | 0