## Burn Down Chart
Project: | Personal Store Application
Sprint # | 3
[5 empty] | DATE: | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Time Left
| Bug fix | N/A | Fixed carousel bug with uneven cards at the end of the list. | Marc | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| R_5 | As a system I would like users to be locked out after 10 failed login attempts. | Add login attempt tracking. | " | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| " | " | Add session tracked lockout status. | " | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| " | " | Add remaining attempts message to login screen. | " | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
| Application Deployment | N/A | Set up initial deployment environment. |  | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
|  |  | Added new DAO classes for deployment. |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 13 | 11.14 | 9.28 | 7.42 | 5.56 | 3.7 | 1.84 | -0.02
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 13 | 12 | 12 | 10 | 6 | 3 | 0 | 0